## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-1 | Setup Python, SQLite & Define Text Type (Customer Feedback) | MUST HAVE | NA | Gopika | 3- Completed
S1 | S1 | US-2 | Implement Text Reading, Chunking & Rule-Based Scoring | MUST HAVE | NA | Gopika | 3- Completed
S1 | S1 | US-3 | Implement Database Storage & Processing Flow | MUST HAVE | NA | Gopika | 3- Completed
S2 | S2 | US-4 | Develop Text Breaker for splitting large text datasets | MUST HAVE | US-3 | Gopika | 3- Completed
S2 | S2 | US-5 | Implement Parallel Text Loader using multiprocessing | MUST HAVE | US-4 | Gopika | 3- Completed
S2 | S2 | US-6 | Test Text Loader with large CSV text files | MUST HAVE | US-5 | Gopika | 3- Completed

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day-6 | Understanding multiprocessing concepts | Studied examples and clarified session
S1 | Day-9 | Minor database error | Debugged and fixed
S2 | Day-2 | Parallel processing errors during testing | Debugged multiprocessing code
S2 | Day-4 | Performance testing with large files slow | Optimized text splitting logic

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | T-1 | Introduction of Project | 2026-02-10 | 2026-02-10 | All | Planning | 3-Completed | 1
US-1 | T-2 | Python Setup &SQLite installation | 2026-02-11 | 2026-02-11 | All | Setup | 3-Completed | 1
US-2 | T-3 | Learn Text Handling& Multiprocessing Concepts | 2026-02-12 | 2026-02-13 | All | Learning | 3-Completed | 2
US-2 | T-4 | Design Processing Flow & Module Structure | 2026-02-14 | 2026-02-15 | All | Design | 3-Completed | 2
US-3 | T-5 | Implement Text Reading, Chunking & Scoring | 2026-02-16 | 2026-02-16 | All | Coding | 3-Completed | 3
US-3 | T-6 | Build Main Processing Pipeline &Database Storage | 2026-02-17 | 2026-02-18 | All | Coding | 3-Completed | 3
US-4 | T-7 | Implement text splitting logic | 2026-02-24 | 2026-02-25 | All | Coding | 3-Completed | 3
US-4 | T-8 | Implement batch text processing | 2026-02-26 | 2026-02-27 | All | Coding | 3-Completed | 2
US-5 | T-9 | Implement multiprocessing loader | 2026-02-28 | 2026-03-01 | All | Coding | 3-Completed | 3
US-5 | T-10 | Integrate loader with text breaker | 2026-03-02 | 2026-03-03 | All | Coding | 3-Completed | 2
US-6 | T-11 | Test system with large text dataset | 2026-03-04 | 2026-03-05 | All | Coding | 3-Completed | 2
US-6 | T-12 | Measure performance improvement | 2026-03-06 | 2026-03-06 | All | Coding | 3-Completed | 2

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-11 | 2026-02-20 | gopika | Start designing architecture before coding | Stop coding without planning | Continue modular programming approach | Practice advanced parallel processing in next milestone
2 | S2 | 2026-02-25 | 2026-03-07 | gopika | Start writing optimized parallel code | Stop testing with very small datasets | Continue modular coding practice | Improve performance testing in next sprint
3
4
5
6
7